| Medical Examiner Service |  |
| --- | --- |

Suggested Actions for Local Authorities in considering how to implement the new Medical Examiner Service

Introduction

This paper is a ‘work in progress’ document which has been prepared by local authority coroner’s and registration managers in consultation with the Department of Health Programme team.

This is not a final document as there is further information and guidance which is still being prepared and additional information will be available in the response to the consultation on the reforms which is yet to be published.

Background

The Coroners and Justice Act 2009 sets out the legal basis for a new system of death certification in England and Wales.  With the abolition of Primary Care Trusts (PCTs) in April 2013, the Health and Social Care Act 2012 transferred responsibility for the new medical examiner service from PCTs to sit with Local Authorities (LAs) in England and Local Health Boards (LHBs) in Wales.  Medical examiner services will need to work on a day to day basis with local coroners and registration services as set out in the regulations proposed for the new system.

All deaths not subject of a coroner investigation will be subject of a medical examiner’s independent scrutiny and confirmation of cause of death stated by an attending doctor.  The reformed system is expected to strengthen safeguards for the public, make the process of death certification simpler and more open for the bereaved.  The running cost of the service is expected to be met through a medical examiner fee charged to the bereaved.  Existing Cremation Forms fees will be abolished as will the role of medical referees.

Objective

Appointing authorities must:

(a) appoint enough medical examiners, and make available enough funds and other resources, to enable those functions to be discharged in its area;

(b) monitor the performance of medical examiners appointed by the Local Authority in England and Local Health Boards in Wales by reference to any standards or levels of performance that those examiners are expected to attain.

We would strongly advise that you read all the resource information prior to setting up the project team so that you are aware of all the background and resources that are available.

Abbreviations

DH – Department of Health

IT – Information Technology

GP – General Practitioner

LA – Local Authority

LGA – Local Government Association

ONS – Office for National Statistics

ME – Medical Examiner

MEO – Medical Examiner Officer

NHS – National Health Service

RESOURCE LIST

| Title | Contents | Location |
| --- | --- | --- |
| Legislation | Legal basis Statutory basis for service | http://www.legislation.gov.uk/ukpga/2009/25/contents Appendix A Link to new legislation to be inserted in due course |
| National Medical Examiner | Website and implementation toolkit available with national guidance and sample 'Exemplar Forms' | There is a medical examiner website which is under construction. A link will be published in due course |
| e-learning | Training modules for medical practitioners and associated professionals – compulsory for Medical Examiners applying for the posts | The link to the e-learning modules will be included when fully operational |
| Cost calculator | To be developed by DH – provides a guide to number of staff required and how much it will cost for your particular ME area |  |
| Reference materials | Francis enquiry | http://webarchive.nationalarchives.gov.uk/20150407084003/http://www.midstaffspublicinquiry.com/ |
| Local statistics | Gather together statistics on your proposed region The Office for National Statistics (ONS) may be able to provide registration and coroner data on numbers and locations | https://www.ons.gov.uk/peoplepopulationandcommunity/birthsdeathsandmarriages/deaths https://www.gov.uk/government/statistics/announcements/coroners-statistics-2015 https://www.gov.uk/search?q=coroners+statistics+2015 Consider an analysis of where deaths occur – hospital, hospice, home etc. Local sources of statistical and demographic data |
| Lessons learnt from the pilot sites | Are there any issues which arise from the lessons learnt from the pilot sites which need to be considered as part of your local approach? Information to be updated ME system in Scotland | https://www.rcpath.org/discover-pathology/public-affairs/medical-examiners.html https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/521226/Death_certificate_reforms_pilots_-_report_A.pdf . |
| National 'exemplar forms' | Sample templates provided as evidence of good practice | There is a medical examiner website which is under construction. A link will be published in due course https://www.gov.uk/government/consultations/death-certification-reforms See below under process guides/forms |

ACTION PLAN/CHECKLIST

| Work Stream | Action | Supporting documents | Comments |
| --- | --- | --- | --- |
| Project governance | Consider how you will set up your project locally; who will be leading it, who will be key board members etc. Some suggestions are listed below: - Appoint lead ME manager - Set up project governance - Sponsor - Project board - Project groups/work streams - Set up local project plan - Project support - Risk and Issues log - Impact assessment | Local project governance and systems National risk register and issue log National impact assessment | The lead manager will be the local contact for the LA and DH A senior officer will need to support the project locally in order to ensure appropriate engagement with all necessary agencies required for implementation |
| Liaison with DH | How will you ensure you receive updates and guidance documents in a timely way? Engagement with Directors of Public Health Ensure named LA contact available for all communications from the DH etc. |  |  |
| Political engagement | How will you seek the support/governance of the Portfolio Holder, Scrutiny Committee or relevant politicians in your locality? |  | Consider what involvement Councillors should have? |
| Stakeholder engagement | Who are your key stakeholders? How will you seek the support of key stakeholders in your area? |  |  |
| Equality impact assessment | What are the needs of your area? Do you have any specific cultural needs? How will you arrange out of hours access to services? | LA Equality policy document and Impact Assessment template |  |
| Finance | Consider what information you need to help you to work out how much income there is to deliver the service and therefore how many staff will be needed - Scope volumes of deaths in proposed area - Number of coroner referrals - Location of deaths - Registration service data on registrations - Population data on long term growth/new builds etc. - Use cost calculator to support estimates for cost and income - What is current debt recovery in the LA - What is current non-payment % Set up budget lines for the DH set up funding Set up a revenue budget for the new service Do you need to set up the new establishment on LA payment and finance system? Consider national monitoring required for the review of the service | DH Cost calculator to be developed |  |
| Options paper | What are the options open to you regarding service delivery? Will you commission the service or will you deliver it through the LA? How will this decision be signed off within your LA? Will you consider working with another LA to deliver the service? How will you ensure the 'independence' of the ME? |  | Consider how the service will be delivered. What geographical, political and NHS/CCG area will it cover? Will the service be commissioned or delivered? |
| Fee collection | How much is the fee? How will the fee be collected? Who will collect the fee? How will reconciliation of fees be done and by whom? LA policy on what procedures will be taken with debtors Could you join with other LA to set up a central collection of the fee? Are there opportunities for a national fee payment mechanism? | Potential for a Voluntary Agreement between Local Authority and Funeral Director (framework may be drafted by DH/Local Government Association (LGA) if funeral directors are willing to enter into a national agreement) | Assumption in Consultation Document is that 80% of fees will be collected by the Funeral Director – Assumption = 2.5% unpaid Assumptions are being considered as part of the consultation Are these reasonable in your local authority? |
| Human Resources | If you are delivering the service consider how you will appoint the ME and MEOs Consider the Job Profile for ME/MEO/Other staff as required which has been developed by DH Consider how validation of the ME will be carried out and verified by the LA How will the LA manage medical staff e.g. the appropriate audit processes, compliance with national guidance and standards, indemnity insurance, peer reviews? Are there any TUPE issues if the bereavement service is involved? Will any out of hours service impact on other existing staff and will this require changes to contracts? | DH and the Local Government Association are developing template job profiles for all roles along with advice and guidance on how to appoint these staff Royal College of Pathologists to offer guidance | The LA may wish to use as exemplars or create their own Consider appointing the ME lead as early as possible as they need to be involved in the design of the local service and the appointment of his/her team |
| Information Technology | Do you know what is already in place in NHS/GP practices/LA? Consider how you will transfer data between the GP/place of death to the ME office Can you identify what is required for the local IT case management solution Do you have a list of preferred providers? Liaise with procurement if a tender is required? Keep abreast of national developments in this area How many computers, phones, mobiles, etc. will you need? What other IT can bring efficiencies (electronic signatures, data transfer)? Which Case Management System will you use? What IT solution will you require for payments? What data do you need from CCGs? Consider what IT they use and whether it is compatible with other users IT for the transfer of data/forms | The National Medical Examiner has developed an Access database Case Management prototype There are also some other providers who are developing case management systems alongside coroner case management systems |  |
| Communications | Identify stakeholders and create contact list of names and contact details Consider how you will engage with them Prepare local briefing literature and website information Work with training group on the briefing and training sessions Ensure that key staff are well briefed on media training and the key messages Public information leaflets, website etc. | DH to provide source/sample leaflets and training documents |  |
| Training | Consider how you will brief and train your key partners. This may include: - Registrars - Medical practitioners - Coroners - Contact centres - Funeral directors - Councillors - Other stakeholders | E-learning modules will be available – http://www.e-lfh.org.uk/programmes/medical-examiner |  |
| Commissioning/ procurement | Consider your service delivery model and if you are to commission the service what you will need to look at: - Direct commissioning of Medical Examiners - Tendering for a contract to collect fee - Tendering for a contract to collect and deliver medical notes - Tendering for a contract to examine bodies - Tendering for an IT contract | Consider using opportunities to share documents LG guidance on commissioning to be developed Local authority procurement guidance |  |
| Quality Assurance/ Performance management | Review the national standards and consider how you will monitor them Will you require local standards? How will you monitor them? You might want to consider the following: - Will you need to set up performance monitoring in line with national guidance from National ME? - Local service standards in line with local Key Performance Indicators - Customer service standards - Complaints and compliments - Monitoring of feedback for continuous improvement - Publishing of results - Liaison with clinical governance teams - Sharing of good practice with other ME services - Identification of local issues and trends | Draft Standards for the Delivery of the Medical Examiner Service |  |
| Processes and procedures | Consider how the service will be delivered locally: - Which locations will be used? - How will patient notes be transported/ electronically shared? - What hours will the service operate? - Shifts? - Out of hours (to meet local and cultural needs) - Local monitoring – forms etc. - Write standard operating procedures - Consider setting up protocols for organ retrieval with the local transplant team, faith groups, paediatric and maternity See separate section below |  |  |
| Risk Management and Business Continuity | Have you considered the risks of implementation and service delivery in your planning? Have you considered Business Continuity Planning? Have you considered contract management? | Corporate Risk Register and Business Continuity template |  |
| Policies | Which policies will you need to develop? Some examples may be: - Induction guidance - Impact Assessments - Faith groups - Health and safety - Non-payment of fee - Complaints – medical - Complaints – customer service - Human Resource policies - Standard Operating Practices |  |  |
| Property | What accommodation is required and where? Do you need facilities for families to meet ME/MEO Accessibility Appropriate for medical practitioners to get to and from Parking Consider whether you will need access to the mortuary and viewing of the deceased? Furniture for office/IT Consider Office opening times |  | Consider Gloucestershire model of incorporating bereavement services |
| Data/ Information management | How will this be achieved – some suggestions to consider are: - Record keeping protocols - Data sharing issues between LA and NHS and Coroner Services and Registrars - Caldicott guardian - Data retention - Access to medical records - Transfer of medical records - IT storage and transfer between LA and NHS and Coroner Services - Clarity of who is the Data Controller for ME services | The National Medical Examiner has developed an Access database which can be used There are private providers developing coroner and ME case management systems |  |
| Examination of the body | Consider how external examination of the body will take place and where How will you pay for the service if it is not the ME? How will you track payments for this service to delegated individuals? Who will carry out the delegated responsibility and how will you ensure that they are accredited and trained? | This is a draft – to be confirmed following consultation |  |
| Monitoring and post implementation | To be confirmed – however will need to be national standard Post implementation review Lessons Learned |  |  |

PROCESS GUIDES/FORMS

| Process | Action | Supporting documents | Comments |
| --- | --- | --- | --- |
| Referral to Medical Examiner | Draft guidance for registered medical practitioners Final Entry in Clinical Record Following a Death | Legislation – examples below Exemplar forms Exemplar forms |  |
| Referral from Medical Examiner to Coroner |  | Legislation – Regulations: 4(1) (2) (3) 3 (6) |  |
| Transmission of documents to Registration Office/Officer | ME-2(A) Medical Examiners' Notification of Confirmed Cause of Death ME-2(B) Medical Examiner's Notification of Certified Cause of Death | Exemplar forms |  |
| Referral from Registrar to Medical Examiner |  |  |  |
| Examination of the body | Local protocols | Source documents to be provided by pilot/DH? |  |
| Body Collection | Good Practice guidance issued | Draft – to be confirmed following consultation |  |
| Publicity and information | How will you publicise and inform key stakeholders and the public? | DH National communications strategy Bereavement leaflets DH information National communications Local meetings and briefing sessions Local press |  |
| Data protection | What legal gateways will enable you to share and receive information or data from others? | National data sharing agreement to be developed DH guidance Exemplar forms for tracking patient records |  |

POST IMPLEMENTATION CONSIDERATIONS

| Benefits Realisation | Contents | Mechanism for Capturing Data/Information |
| --- | --- | --- |
| Training to Medical Practitioners | Ongoing training to new medical practitioners Training related to Medical Examiner local findings |  |
| Coroners Service | Collecting evidence of impact on workload, volumes, and costs both positive and negative |  |
| Customer Satisfaction | Compliment and complaint handling – monitoring feedback and impact |  |
| Clinical Governance | Improved local mortality data and intelligence Improved national mortality data and intelligence |  |
| New Burdens Assessment | Collection of data/evidence |  |

Appendix A – Coroners and Justice Act 2009

CHAPTER 2

NOTIFICATION, CERTIFICATION AND REGISTRATION OF DEATHS

18 Notification by medical practitioner to senior coroner

(1) The Lord Chancellor may make regulations requiring a registered medical practitioner, in prescribed cases or circumstances, to notify a senior coroner of a death of which the practitioner is aware.

(2) Before making regulations under this section the Lord Chancellor must consult—

(a) the Secretary of State for Health, and

(b) the Chief Coroner.

19 Medical examiners

(1) Primary Care Trusts (in England) and Local Health Boards (in Wales) must appoint persons as medical examiners to discharge the functions conferred on medical examiners by or under this Chapter.

(2) Each Trust or Board must—

(a) appoint enough medical examiners, and make available enough funds and other resources, to enable those functions to be discharged in its area;

(b) monitor the performance of medical examiners appointed by the Trust or Board by reference to any standards or levels of performance that those examiners are expected to attain.

(3) A person may be appointed as a medical examiner only if, at the time of the appointment, he or she—

(a) is a registered medical practitioner and has been throughout the previous 5 years, and

(b) practises as such or has done within the previous 5 years.

(4) The appropriate Minister may by regulations make—

(a) provision about the terms of appointment of medical examiners and about termination of appointment;

(b) provision for the payment to medical examiners of remuneration, expenses, fees, compensation for termination of appointment, pensions, allowances or gratuities;

(c) provision as to training—

(i) to be undertaken as a precondition for appointment as a medical examiner;

(ii) to be undertaken by medical examiners;

(d) provision about the procedure to be followed in connection with the exercise of functions by medical examiners;

(e) provision conferring functions on medical examiners;

(f) provision for functions of medical examiners to be exercised, during a period of emergency, by persons not meeting the criteria in subsection (3).

(5) Nothing in this section, or in regulations under this section, gives a Primary Care Trust or a Local Health Board any role in relation to the way in which medical examiners exercise their professional judgment as medical practitioners.

(6) In this section “the appropriate Minister” means—

(a) in relation to England, the Secretary of State;

(b) in relation to Wales, the Welsh Ministers.

(7) For the purposes of this section a “period of emergency” is a period certified as such by the Secretary of State on the basis that there is or has been, or is about to be, an event or situation involving or causing, or having the potential to cause, a substantial loss of human life throughout, or in any part of, England and Wales.

(8) A certification under subsection (7) must specify—

(a) the date when the period of emergency begins, and

(b) the date when it is to end.

(9) Subsection (8)(b) does not prevent the Secretary of State certifying a new period of emergency in respect of the same event or situation.

20 Medical certificate of cause of death

(1) The Secretary of State may by regulations make the following provision in relation to a death that is required to be registered under Part 2 of the 1953 Act—

(a) provision requiring a registered medical practitioner who attended the deceased before his or her death (an “attending practitioner”)—

(i) to prepare a certificate stating the cause of death to the best of the practitioner’s knowledge and belief (an “attending practitioner’s certificate”), or

(ii) where the practitioner is unable to establish the cause of death, to refer the case to a senior coroner;

(b) provision requiring a copy of an attending practitioner’s certificate to be given to a medical examiner;

(c) provision allowing an attending practitioner, if invited to do so by the medical examiner or a registrar, to issue a fresh attending practitioner’s certificate superseding the existing one;

(d) provision requiring a senior coroner to refer a case to a medical examiner;

(e) provision requiring a medical examiner to make whatever enquiries appear to be necessary in order to confirm or establish the cause of death;

(f) provision requiring a medical examiner to whom a copy of an attending practitioner’s certificate has been given—

(i) to confirm the cause of death stated on the certificate and to notify a registrar that the cause of death has been confirmed, or

(ii) where the examiner is unable to confirm the cause of death, to refer the case to a senior coroner;

(g) provision for an attending practitioner’s certificate, once the cause of death has been confirmed as mentioned in paragraph (f), to be given to a registrar;

(h) provision requiring a medical examiner to whom a case has been referred by a senior coroner—

(i) to issue a certificate stating the cause of death to the best of the examiner’s knowledge and belief (a “medical examiner’s certificate”) and to notify a registrar that the certificate has been issued, or

(ii) where the examiner is unable to establish the cause of the death, to refer the case back to the coroner;

(i) provision for a medical examiner’s certificate to be given to a registrar;

(j) provision allowing a medical examiner, if invited to do so by the registrar, to issue a fresh medical examiner’s certificate superseding the existing one;

(k) provision requiring a medical examiner or someone acting on behalf of a medical examiner—

(i) to discuss the cause of death with the informant or with some other person whom the examiner considers appropriate, and

(ii) to give him or her the opportunity to mention any matter that might cause a senior coroner to think that the death should be investigated under section 1;

(l) provision for confirmation to be given in writing, either by the informant or by a person of a prescribed description, that the requirement referred to in paragraph (k) has been complied with;

(m) provision prescribing forms (including the form of an attending practitioner’s certificate and of a medical examiner’s certificate) for use by persons exercising functions under the regulations, and requiring the forms to be made available to those persons;

(n) provision requiring the Chief Medical Officer of the Department of Health, after consulting—

(i) the Officer with corresponding functions in relation to Wales,

(ii) the Registrar General, and

(iii) the Statistics Board,

to issue guidance as to how certificates and other forms under the regulations are to be completed;

(o) provision for certificates or other forms under the regulations to be signed or otherwise authenticated.

(2) Regulations under subsection (1) imposing a requirement—

(a) may prescribe a period within which the requirement is to be complied with;

(b) may prescribe cases or circumstances in which the requirement does, or does not, apply (and may, in particular, provide for the requirement not to apply during a period of emergency).

(3) The power under subsection (1)(m) to prescribe forms is exercisable only after consultation with—

(a) the Welsh Ministers,

(b) the Registrar General, and

(c) the Statistics Board.

(4) Regulations under subsection (1) may provide for functions that would otherwise be exercisable by a registered medical practitioner who attended the deceased before his or her death to be exercisable, during a period of emergency, by a registered medical practitioner who did not do so.

(5) The appropriate Minister may by regulations provide for a fee to be payable to a Primary Care Trust or Local Health Board in respect of—

(a) a medical examiner’s confirmation of the cause of death stated on an attending practitioner’s certificate, or

(b) the issue of a medical examiner’s certificate.

(6) Section 7 of the Cremation Act 1902 (c. 8) (regulations as to burning) does not require the Secretary of State to make regulations, or to include any provision in regulations, if or to the extent that he or she thinks it unnecessary to do so in consequence of—

(a) provision made by regulations under this Chapter or by Coroners regulations, or

(b) provision contained in, or made by regulations under, Part 2 of the 1953 Act as amended by Part 1 of Schedule 21 to this Act.

(7) In this section—

“the appropriate Minister” has the same meaning as in section 19; “informant”, in relation to a death, means the person who gave particulars concerning the death to the registrar under section 16 or 17 of the 1953 Act; “period of emergency” has the same meaning as in section 19; “the Statistics Board” means the body corporate established by section 1 of the Statistics and Registration Service Act 2007 (c. 18).

21 National Medical Examiner

(1) The Secretary of State may appoint a person as National Medical Examiner.

(2) The National Medical Examiner is to have—

(a) the function of issuing guidance to medical examiners with a view to securing that they carry out their functions in an effective and proportionate manner;

(b) any further functions conferred by regulations made by the Secretary of State.

(3) Before appointing a person as National Medical Examiner or making regulations under subsection (2)(b), the Secretary of State must consult the Welsh Ministers.

(4) A person may be appointed as National Medical Examiner only if, at the time

of the appointment, he or she—

(a) is a registered medical practitioner and has been throughout the previous 5 years, and

(b) practises as such or has done within the previous 5 years.

(5) The appointment of a person as National Medical Examiner is to be on whatever terms and conditions the Secretary of State thinks appropriate.

(6) The Secretary of State may pay to the National Medical Examiner—

(a) amounts determined by the Secretary of State by way of remuneration or allowances;

(b) amounts determined by the Secretary of State towards expenses incurred in performing functions as such.

(7) The National Medical Examiner may amend or revoke any guidance issued under subsection (2)(a).

(8) The National Medical Examiner must consult the Welsh Ministers before issuing, amending or revoking any such guidance.

(9) Medical examiners must have regard to any such guidance in carrying out their functions.

Amended by the Health and Social Care Act – responsibilities transfer to upper-tier local authorities.